## Slide 1
Project IFDA – Status Report
Date: | 02/19/2021 | Overall Status:
Team: | Malik Khan, Echo Luan, Lanyi Xu, Yanxi Zhou, Xiaofan Zhu | 
Project Description: | Determine pain points and relevant information using internal and public data to strategize a recruitment and retention improvement plan for foodservice distributors(IFDA members).
Status Summary
Scheduled meetings with project advisors and had a better understanding of the project and the roles of the team Presented what we knew so far and our approaches with IFDA members in the kickoff meeting Confirmed detailed interview information with Annika
Workstream: | Trend | Comments:
Meetings within the group and with advisors |  | - Had several group meetings to discuss presentation slides and brainstorm interview questions - Set regular meetings with Professor Junke and Jamie to discuss our progress and hear feedback
Kickoff Meeting |  | -The team introduced our program, ourselves and high level plan with IFDA members -Confirmed contact information and next steps with Annika and Mark
Interview Questions |  | - Draft interview questions in internal and external document - Showed drafts to IFDA, but there are some unclarities that need to be revised
Date | Recent Accomplishments & Updates:
02/14 | Group meeting, work is evenly distributed
02/15 | Met Professor Junker, gained professional feedback on the current work and future steps
02/16 | Met Jamie and rehearsed kickoff presentation
02/17 | Kickoff meeting with IFDA members
Date | Issue: | Assigned To: | Due:
Date | Upcoming High-Level Activities:
02/18 | Each group member will read and watch more background materials about the warehouse industry
02/19 | Group meeting to revise and finalize interview questions (will send to Annika)
2/26 | Conduct Pilot Interview with Jeff and the PFG team.